## Sheet1
1. Authentication & User Management
Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority
Role-Based Access Control | US-UM-01 | As an administrator, I want to assign role-based access permissions so that users can access only authorized functionalities. | Users should only access features based on assigned roles. | 8 | High
User Registration | US-UM-02 | As a customer, I want to register using my mobile number, email address, and identity details so that I can create an account and access housing loan services securely. | Customer account should be created successfully after validating all mandatory details. | 5 | High
Secure Login | US-UM-03 | As a customer, I want to log in using a password and OTP authentication so that my account and loan information remain protected. | User should be authenticated successfully using valid credentials and OTP. | 5 | High
Password Management | US-UM-04 | As a customer, I want to reset and change my password securely so that I can regain access to my account whenever required. | Password should be updated only after successful identity verification. | 3 | Medium
Profile Management | US-UM-05 | As a customer, I want to manage my personal, employment, and financial information so that my profile remains accurate and up to date. | User should be able to view, update, and save profile details successfully. | 5 | High
2. Advanced Eligibility Assessment & CIBIL Analysis
Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority
Eligibility Assessment | US-EL-01 | As a customer, I want the system to calculate my housing loan eligibility so that I can determine whether I qualify for a loan. | Eligibility should be calculated accurately based on financial inputs. | 8 | High
CIBIL Score Integration | US-EL-02 | As a customer, I want my CIBIL score to be considered during eligibility assessment so that I can understand its impact on loan approval. | CIBIL score should be considered in eligibility calculation. | 8 | High
Debt-to-Income Ratio Calculation | US-EL-03 | As a customer, I want the system to calculate my Debt-to-Income ratio so that my repayment capability can be evaluated accurately. | DTI ratio should be calculated and displayed correctly. | 5 | High
Eligibility Result Display | US-EL-04 | As a customer, I want to view my eligibility status so that I can understand my loan approval chances. | Status should display Eligible, Conditionally Eligible, or Not Eligible. | 3 | High
Eligibility Explanation Engine | US-EL-05 | As a customer, I want detailed explanations for loan rejection or conditional approval so that I can identify areas for improvement. | Appropriate reasons should be displayed for each result. | 8 | High
Improvement Recommendations | US-EL-06 | As a customer, I want suggestions to improve my eligibility so that I can increase my chances of obtaining a housing loan. | Personalized recommendations should be generated. | 5 | High
Eligibility Simulation | US-EL-07 | As a customer, I want to simulate different loan amounts and tenures so that I can explore multiple eligibility scenarios. | Updated eligibility results should be generated instantly. | 8 | Medium
Maximum Loan Determination | US-EL-08 | Determine the maximum housing loan amount that can be approved without requiring a mortgage. The result should be displayed clearly to the customer. | System displays maximum eligible loan amount accurately. | 8 | Critical
3. Loan Guidance & Recommendation Engineer
Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority
Loan Product Information | US-LG-01 | As a customer, I want information about available housing loan products so that I can understand my borrowing options. | All loan products and descriptions should be displayed. | 5 | Medium
Loan Type Classification | US-LG-02 | As a customer, I want loan products to be categorized by type so that I can easily identify the most relevant option. | Loan categories should be displayed correctly. | 3 | Medium
Loan Recommendation | US-LG-03 | As a customer, I want personalized loan recommendations so that I can choose the most suitable loan product. | Recommendations should match customer profile and eligibility. | 8 | High
Product Comparison | US-LG-04 | As a customer, I want to compare multiple loan products so that I can make informed borrowing decisions. | Product comparison should display key differences clearly. | 5 | Medium
Eligibility-Based Recommendations | US-LG-05 | As a customer, I want recommendations based on my eligibility results so that I can focus on achievable loan options. | Recommended products should align with eligibility status. | 5 | High
Loan Guidance Assistant | US-LG-06 | As a customer, I want guidance on EMI, tenure, and repayment options so that I can select the best loan plan. | Guidance information should be displayed accurately. | 5 | Medium
4. Digital Loan Application Management
Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority
Online Loan Application | US-LA-01 | As a customer, I want to submit a housing loan application online so that I can avoid manual paperwork and branch visits. | Loan application should be submitted successfully after validation. | 8 | High
Document Upload | US-LA-02 | As a customer, I want to upload income, employment, and property documents digitally so that the verification process becomes faster. | Documents should be uploaded and stored securely. | 8 | High
Document Validation | US-LA-03 | As a customer, I want mandatory documents to be validated automatically so that incomplete applications are prevented. | System should identify and notify missing mandatory documents. | 5 | High
Application Review | US-LA-04 | As a customer, I want to review my application before submission so that I can ensure all information is accurate. | Application details should be displayed for review before submission. | 3 | Medium
Application Tracking Number | US-LA-05 | As a customer, I want a unique application tracking number so that I can monitor my application status. | Unique application reference number should be generated automatically. | 3 | High
Draft Saving | US-LA-06 | As a customer, I want to save incomplete applications as drafts so that I can complete them later. | Draft applications should be saved and retrieved successfully. | 5 | Medium
5. Loan Status Tracking & Workflow Visibility
Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority
Real-Time Status Tracking | US-LT-01 | As a customer, I want to track my loan application in real time so that I can monitor progress without contacting the bank. | Application status should be updated in real time. | 8 | High
Stage Visibility | US-LT-02 | As a customer, I want to view all loan processing stages so that I can understand the current status of my application. | All workflow stages should be displayed clearly. | 5 | High
Stakeholder Assignment Tracking | US-LT-03 | As a customer, I want to know which officer, engineer, or department is handling my application so that I have complete process transparency. | Current stakeholder information should be displayed accurately. | 5 | High
Pending Task Visibility | US-LT-04 | As a customer, I want to see pending tasks and required actions so that I can complete them on time. | Pending actions should be visible to the customer. | 5 | High
Expected Completion Date | US-LT-05 | As a customer, I want to view expected completion dates for each stage so that I can plan accordingly. | Estimated completion dates should be displayed for every stage. | 8 | High
Workflow Timeline View | US-LT-06 | As a customer, I want a visual workflow timeline so that I can track completed and upcoming activities. | Timeline should display completed, current, and upcoming stages. | 8 | High
Turnaround Time Tracking | US-LT-07 | As a manager, I want processing time for each workflow stage to be tracked so that operational efficiency can be monitored. | Turnaround time reports should be generated accurately. | 8 | Medium
6. Mortgage Requirement Calculation
Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority
Mortgage Value Calculation | US-MRC-01 | Calculate the mortgage value required when a customer requests a loan amount beyond the unsecured eligibility limit. The calculation should follow banking guidelines. | Mortgage requirement is calculated accurately. | 8 | Critical
Property Evaluation | US-MRC-02 | Enable evaluation and verification of property value before accepting it as mortgage security. Property information should be recorded for loan processing. | Property valuation is recorded successfully. | 5 | High
Loan-to-Mortgage Analysis | US-MRC-03 | Analyze the relationship between requested loan amount and available mortgage value. The system should determine whether the collateral is sufficient. | Ratio is calculated and displayed correctly. | 5 | High
Mortgage Requirement Display | US-MRC-04 | Display mortgage requirements clearly so customers understand the collateral needed for higher loan amounts. Information should be presented in an easy-to-understand format. | Mortgage requirement details are shown clearly. | 3 | High
Mortgage Record Management | US-MRC-05 | Maintain mortgage-related records including property details, valuation reports, and mortgage agreements. Records should be securely stored and easily retrievable. | Mortgage records can be stored and updated securely. | 5 | High
7. Loan Repayment Monitoring
Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority
EMI Payment Tracking | US-LRM-01 | As a customer, I want the system to track my EMI payments so that I can monitor my repayment status. | EMI payments are recorded successfully. Payment status is updated after each transaction. Invalid payment entries are rejected. | 3 | High
Repayment Schedule Management | US-LRM-02 | As a customer, I want the system to maintain my repayment schedule so that I can know upcoming installments. | Repayment schedule is generated automatically. Schedule displays due dates and EMI amounts | 5 | High
Outstanding Balance Monitoring | US-LRM-03 | As a customer, I want the system to monitor my outstanding balance so that I can track my remaining loan amount. | Outstanding balance updates after every payment. Balance cannot become negative. | 3 | High
Due Date Tracking | US-LRM-04 | As a customer, I want the system to track due dates so that I can avoid missing payments. | Due dates are displayed correctly. Overdue status is marked automatically | 5 | High
Payment History Management | US-LRM-05 | As a bank officer, I want the system to maintain payment history so that repayment records can be reviewed anytime | Complete payment history is stored and retrievable. Records cannot be modified without authorization | 3 | Medium
8. Notification & Communication Management
Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority
Application Status Notifications | US-NM-01 | As a customer, I want to receive application status notifications so that I stay informed throughout the loan process. | Notifications should be sent whenever the application status changes. | 5 | High
Document Request Alerts | US-NM-02 | As a customer, I want alerts when additional documents are required so that I can avoid processing delays. | Document request alerts should be sent immediately. | 3 | Medium
Approval and Rejection Notifications | US-NM-03 | As a customer, I want notifications regarding approval or rejection decisions so that I can take appropriate action. | Approval and rejection notifications should be delivered successfully. | 3 | High
Reminder Notifications | US-NM-04 | As a customer, I want reminder notifications for pending activities so that I do not miss important deadlines. | Automated reminders should be sent before deadlines. | 5 | Medium
Multi-Channel Communication | US-NM-05 | As a customer, I want communication through SMS, email, and in-app notifications so that I can receive updates through my preferred channel. | Notifications should be supported across all configured channels. | 8 | Medium
9. Post-Disbursement Service Management
Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority
Online Service Request Submission | US-PD-01 | As a customer, I want to submit post-disbursement service requests online so that I do not need to visit the bank physically. | Service requests should be created and tracked successfully. | 8 | High
Digital Engineer Request | US-PD-02 | As a customer, I want to request engineer inspections digitally so that inspection processes become more convenient. | Engineer requests should be submitted successfully. | 8 | High
Engineer Assignment | US-PD-03 | As a manager, I want engineers to be assigned automatically so that service requests are handled efficiently. | Engineers should be assigned based on availability. | 5 | Medium
Digital Inspection Reports | US-PD-04 | As an engineer, I want to upload inspection reports digitally so that approvals can be processed faster. | Inspection reports should be uploaded successfully. | 8 | High
Electronic Sign-Off | US-PD-05 | As an engineer, I want to provide electronic approvals and sign-offs so that paperwork is reduced. | Digital approvals should be recorded securely. | 5 | High
Post-Disbursement Workflow Tracking | US-PD-06 | As a customer, I want to track post-disbursement workflows so that I know the status of my requests. | Workflow progress should be visible in real time. | 8 | High
Service Request Status Updates | US-PD-07 | As a customer, I want real-time updates on service requests so that I remain informed about progress. | Status updates should be displayed immediately after changes. | 5 | High
Digital Document Exchange | US-PD-08 | As a customer, I want to exchange documents digitally with stakeholders so that the process becomes paperless. | Documents should be uploaded, shared, and downloaded securely. | 8 | High
10.Default Management and Notice Generation
Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority
Overdue Loan Detection | US-DMNG-01 | As a bank officer, I want the system to identify overdue loans so that default cases can be handled promptly. | Loans exceeding due dates are marked overdue automatically. | 5 | High
Default Notice Generation | US-DMNG-02 | As a bank officer, I want the system to generate default notices automatically so that customers are informed of overdue payments | Notice is generated immediately after default conditions are met. Notice contains customer and loan details. | 8 | High
Notice Tracking | US-DMNG-03 | As a bank officer, I want the system to track issued notices so that delivery status can be monitored. | Notice status shows Sent, Delivered, or Failed. Tracking records are maintained. | 5 | Medium
Default Escalation Management | US-DMNG-04 | As a bank officer, I want the system to manage escalation procedures so that repeated defaulters receive appropriate actions. | Escalation rules are triggered after predefined default limits | 8 | High
Default Status Monitoring | US-DMNG-05 | As a bank officer, I want the system to monitor defaulted accounts so that recovery actions can be managed effectively. | Default status is updated automatically. Status changes are logged | 5 | High
11.Auction Management
Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority
Auction Eligibility Verification | US-AM-01 | As a bank officer, I want the system to verify auction eligibility so that only valid mortgaged assets are auctioned. | Eligibility rules are validated before auction initiation | 5 | High
Asset Auction Initiation | US-AM-02 | As a bank officer, I want the system to initiate asset auctions so that loan recovery can begin. | Auction can be started only for eligible assets. Auction details are recorded. | 8 | High
Auction Status Tracking | US-AM-03 | As a bank officer, I want the system to track auction status so that progress can be monitored. | Status updates are reflected in real time | 5 | Medium
Auction Recovery Management | US-AM-04 | As a bank officer, I want the system to manage loan recovery through auctions so that outstanding dues can be recovered. | Recovery amount is linked to auction results. Recovery status is updated. | 8 | High
Auction Record Management | US-AM-05 | As a bank officer, I want the system to maintain auction records so that all auction activities are auditable. | Auction records are stored securely and retrievable | 3 | Medium